## Template Guide
Template Guide
What Is a RACI?
A RACI Matrix depicts who (by project role) is responsible (R), accountable (A), consulted (C) and informed (I) for each major project activity.
Why a RACI Matrix?
The RACI Matrix is a helpful way to document and clarify roles and responsibilities on a project.
How to Use This Template
Use this template to document for each project role, who is: 1) Responsible, or owns the execution of the work task. 2) Accountable, or is ultimately accountable for the approval of the work task. 3) Consulted, or provides support in the execution of the work task. 4) Informed, or is informed of the progress and/or final outcome of the work task. As you use this template: 1) Replace the example tasks with the major work tasks included in your project plan. 2) Update the project roles to include all of the major stakeholder groups for your project. 3) Input R, A, C or I to select the appropriate role; the worksheet will automatically color code the cell for you. 4) Save often, as status fields update automatically upon saving.

## Template RACI
RACI Matrix
Project Roles
PROJECT PHASES | (R) = Responsible: Owns the execution of the work task (potentially in collaboration with other team members). (A) = Accountable: Ultimately accountable for the approval of the work task. (C) = Consulted: Provides support in the execution of the work task. (I) = Informed: Informed of the progress and/or final outcome of the work task. | Project Sponsor/ Business Owner | Project Steering Committee | Project Manager | Functional Lead | Technical Lead | Subject Matter Experts | Vendor
| Work Task | R | A | C | I
Project Initiation | Define project organization and roles and responsibilities
Develop and approve charter
Secure vendors/service providers
Complete project initiation checklist
Project Planning | Develop and approve work plan and schedule
Develop and approve budget plan
Develop and approve communication and change management plan
Develop and approve project management plan
Develop and approve benefits measurement plan
Project Execution | Conduct project kickoff
Manage risks, issues, action items, and decisions
Validate and refine requirements
Conduct design activities
Conduct configuration activities
Conduct data conversion activities
Develop interfaces
Develop reports and dashboard displays
Conduct testing
Complete system documentation
Develop user manuals and training materials
Train
Conduct final pre go-live checklist
Go live
Conduct stabilization activities
Project Monitoring/Control | Conduct regular project status meetings
Monitor and report project status
Manage change requests
Project Closeout | Closeout project
Document lessons learned
Transfer to operational support
Validate benefits measurement plan
Archive project documents
Complete project closeout checklist

## Role Definition (hidden)
| Role | Role Definition | ION Role Assignment | Cargill Role Assignment
Cargill Integration | TT Program Mgr | The Cargill program manager provides integrated governance and oversight for a collection of projects with a common goal or success "vision”. These projects consist of people, technology, and processes aimed at implementing significant (strategic) business and/or technology change. Projects within the program have a defined scope and timeline. The program manager's primary focus is to facilitate cross team communication, dependency alignment, issue resolution, and project manager coaching. Program manager is also responsible for overall delivery against financial committment, timeline and scope. | Julie Seifert | Wendy Slagle
| Treasury Program Mgr | The Treasury program manager manages the portfolio of projects across all of Treasury and managing business side resources, aligining business leaders and providing financial spend to NA Controller for project planning purposes. |  | Lisa Osteraas
| Business Lead | The business lead drives project direction and strategy across business leaders and SMEs to ensure clear objectives, requirements and decisions are made in a timely manner. Also engages key stakeholders who are required for decisions or impacted by changes of the project. |  | Jeremy Kidd
| Steering Committee | The Steering Group is a collection of senior management or key stakeholders with the primary responsibility of both Product, Project, and Client Management for Cargill. The Steering Group will facilitate resolution for issues in these areas. In addition, by reviewing status reports and attending a monthly report out meeting, the Steering Group will guide troubled projects to a successful outcome. The Steering Group should be made up of a "Core Group" as well as Cargill representatives. | Michael Kolman | Susan Mercer Judith Mawhood Chad Jurgens Luc Moors
| Inc/Ltd Regional Leadership | Individuals on Regional Leadership team have responsibility of impacted teams/processes driven by program. | N/A | Daryl Wikstrom – NA Treasurer Rahul Gupta – Asst. Regional Treasurer Rachael Johnson – EMEA Cash Mgmt. Alison Mulholland – EMEA Tsy Controller Beth Ward* – NA Cash Mgmt. Lead Shelley Hartman – NA Tsy Controller Shirley Kneale – Cargill Ltd. Treasurer
| Program Controller | Creates financial commitment for submission and tracks program spend. | N/A | Shelley Hartmann
| IT Delivery Lead | Oversees IT project delivery to ensure methodology/best practice is followed and assists with removing roadblocks. | N/A | Taye Mohler
| Application Strategy & Governance | Oversees IT application strategy and agreements across portfolio. | N/A | Marisa Ragsdale
| BRM | Business Relation Management representative . . . | N/A | Sara Petersen
| Enterprise Process Management - Treasury |  | N/A | Susan Jirsa
| CoE | Cargill Treasury Center of Expertise focused on RUN support/maintenance and small projects related to WSS apps. | N/A | Mandi Laing - TSY Pauline Jezierski - Global IT
| Domain Owners | Domain owner is responsible for the global operating model decsiions wihtin their scope of responsibility; including obtaining alignment with other regional leaders and stakeholders. | N/A | Rahul Gupta – FX/Funding Nagam Al-Khadi – Operations Tracey Brazier – Cash Management Alison Mulholland – Accounting Shelley Hartman – Trading Group
| Functional Mgr | Functional manager applies to the group manager for each team member. In most cases, functional managers also sit on the Steering Group. The purpose of showing a separate role is to demonstrate there are multiple avenues for coaching and guidance and should be used prior to escalating to the Steering Group. | Direct manager of team members TBD | Direct manager of team members - Chad Jurgens (TSY) - Pauline Jezierski (IT) - Jason Kabe (IT) ------------------------------------ - Luc Moors (IT) - Susan Mercer (TSY) - Judith Mawhood (TSY)
| WMST | Wallstreet Managed Services acts as the IT group for hosted ASP clients. They perform all client hardware and software installations, system down time, back-up and recovery, etc. in all client test and production environments. When a local install is performed, WMST is "replaced" with the Client's Technical Infrastructure Team. | -Mark Tirschwell -Rob Kane -Jason Chang | - Eric Lampert (Solution Architect) - TBD (EAI) - Matt Pankratz (TGRC) - Kevin Heller (Technical Lead) - Wendy Slagle (Pgm Mgr/PM) - ION PS Team as necessary
| Client Support | The Client Support team is the fist and second line support team for application/product issue faced by the client once the client is live with Cargill. This team will play a role in the Client Implementation Teams during Go-Live, Production Transition, and Production. | CS Team Keith Threadgold, Fernando Lucena | CoE Team Leads: Pauline Jezierski (IT); Mandi Laing (TSY) - TCS Support - JDE Support - Others to be defined during Planning Phase/Gate
| CCE | Cargill training and communications team responsible for supporting the organization with change management analysis, creation and delivery through implementation |  | TBD (CCE Cnsultant)
| ION Training Dept | The ION training and education department responsible for providing Cargill training to clients and internal client delivery teams. | Daniela Anzarouth
Cargill Project | Project Mgr (PM) | A single project lead / manager responsible for managing a successful client delivery when a project may span cross-functional teams. This person manages scope, resource utilization, task assignment and status, risk, issues, planning and scheduling, and client expectations. Project leads / managers also sit on the Steering Group. | 1. TILT Implementation - TBD 2. T-ARC Implementation - TBD 3. Detailed Planning - TBD | 1. TILT Implementation - TBD 2. T-ARC Implementation - TBD 3. Detailed Planning - TBD
| ION Analysts/BCs | Multiple business analyst assigned to support the demands of the project. Resources are assigned/allocated by the project leads and/or project managers (and in most cases functional managers). The analysts are client facing but are also expected to be collaborative with internal cross functional teams. | Multiple assigned per client project | N/A
| Design Leads |  | N/A | Shirley Kneale – FX/Funding Lesley Phillips – Operations Jonine Husted – Cash Management Marie Higgins – Accounting Lori Spaeth – Reporting Crystal Tan – LC/Gtee
| TSY Analyst |  | N/A | Christian Bertolotto – ACM Tag/Solution Integrity Lead Hannah Miller – TRM tag Josie Knorr – CMM Tag/Security Model
| Data & Reporting Lead |  | N/A | Sue Foster - IT Lori Spaeth - Business
| Data Migration Lead |  | N/A | Steph Sipprell
| Technical Lead |  | N/A | Kevin Heller
| Solution Design Architects |  | N/A | Eric Lampert Chad Wagner
| Architect |  | N/A | Jess Olson
| Integration Lead |  | N/A | TBD
| ION Developer / TCs | Multiple technical developers assigned to support the demands of the project. Resources are assigned/allocated by the project leads and/or project managers (and in most cases functional managers). The developers can be client facing and are also expected to be collaborative with internal cross functional teams. | Multiple assigned per client project | N/A
| Acct Mgt | The account manager or team for the client project implementation. | Michael Kolman | N/A
Note on D2: Julie Seifert: Suggested at this point; to be discussed, reviewed and agreed.
Note on E2: Julie Seifert: Suggested at this point; to be discussed, reviewed and agreed.