## Template Guide
Template Guide
What Is a RAID Document?
A RAID workbook documents all project-related decisions, action items, issues, and risks (RAID).
Why a RAID?
The RAID workbook provides a single tool for project managers to document project-related decisions, track the status of action items and issues, and document known project risks.
How to Use This Template
Use this template to document: 1) Risks (Tab 1). Any known event which may adversely impact project outcomes. If realized, a risk often becomes an issue which requires resolution. 2) Action Items (Tab 2). Work not originally in the project work plan that requires follow up. Action items may have an impact to the schedule or require additional resources or expertise to complete. 3) Issues (Tab 3). Any items that will have an adverse impact on the project if left unresolved. Issues can arise from realized risks. An issue will likely require a decision to be made from several alternatives and may result in one or more action items. 4) Decisions (Tab 4). Project-related decisions. Decisions often resolve an issue and may result in action items. Decisions may alter assumptions or constraints, impact the project approach, or change business processes. As you use this template: 1) Click on the header row cells for more detailed instructions on how to complete each worksheet. 2) Where available, use the drop-down menus to select an appropriate response. 3) Save often, as status fields (e.g., open/closed action items, open/closed issues, risk exposure rating) update automatically upon saving. 4) Use the available filters to customize worksheet views (e.g., view action items assigned to only a specific person or only open issues).

## 1. Risks
Risk Register
Risk Summary | [7 empty] | Risk Exposure |  |  | Risk Response Plan |  |  | Contingency Plans
# | Status | Risk Category | Risk Title | Risk Description | Risk Impact Description | Date Identified | Raised By | Probability | Impact | Rating | Strategy | Response Description | Assigned To | Contingency Plan | Trigger Decritpion | Comments/Status Updates
R-01 | Active | Resource | Technical resource constraints | Two key technical SMEs -- also assigned to other projects due to begin during the course of this project -- risk their availabilty to complete critical path activities for this project according to schedule. | If nothing is done to mitigate the risk, this will result in schedule delays. | 2019-12-31 | Jane Doe | 3 | 3 | 9 | Mitigate | Coordinate the timing of the technical activities across projects to eliminate conflicts; revisit project priority to assign resources to the highest priority project first. | Jane Doe | Work with leadership to either approve schedule change request, or acquire additional resources. | Resource not available per schedule.
R-02
R-03
R-04
R-05
R-06
R-07
R-08
R-09
R-10
R-11
R-12
R-13
R-14
R-15
R-16
R-17
R-18
R-19
R-20
R-21
R-22
R-23
R-24
R-25
R-26
R-27
R-28
R-29
R-30
R-31
R-32
R-33
R-34
R-35
R-36
R-37
R-38
R-39
R-40
R-41
R-42
R-43
R-44
R-45
R-46
R-47
R-48
R-49
R-50

## 2. Action Items
Action Item Log
# | Action Item | Assigned To | Date Assigned | Date Due | Date Completed | Status | Comments/Status Updates
A-01 | SAMPLE - Complete scope change request for additional module functionality. | John Smith | 2019-01-01 | 2019-01-31 | 2019-01-31 | Closed | Completed impact analysis for requested scope change 1/15/31.
A-02
A-03
A-04
A-05
A-06
A-07
A-08
A-09
A-10
A-11
A-12
A-13
A-14
A-15
A-16
A-17
A-18
A-19
A-20
A-21
A-22
A-23
A-24
A-25
A-26
A-27
A-28
A-29
A-30
A-31
A-32
A-33
A-34
A-35
A-36
A-37
A-38
A-39
A-40
A-41
A-42
A-43
A-44
A-45
A-46
A-47
A-48
A-49
A-50

## 3. Issues
Issues Log
# | Category | Issue Title | Issue Description | Issue Impact | Assigned To | Priority | Date Identified | Due Date | Resolution Date | Resolution/Action Plan | Status | Comments/Status Updates
I-01 | Training | Delayed training materials | The project resource assigned to develop training materials has been unexpectedly pulled from the project, impacting the team's ability to complete this task on schedule. | Training materials will be delayed. | John Smith | Medium | 2019-01-01 | 2019-01-31 | 2019-01-31 | The vendor will provide training materials at an additional cost. | Closed | Also considered: 1) Delaying training; and 2) Reassigning this task. Due to the time criticality of go live and the unavailability of additional resources, TPU will process a scope change to include this as a vendor task.
I-02
I-03
I-04
I-05
I-06
I-07
I-08
I-09
I-10
I-11
I-12
I-13
I-14
I-15
I-16
I-17
I-18
I-19
I-20
I-21
I-22
I-23
I-24
I-25
I-26
I-27
I-28
I-29
I-30
I-31
I-32
I-33
I-34
I-35
I-36
I-37
I-38
I-39
I-40
I-41
I-42
I-43
I-44
I-45
I-46
I-47
I-48
I-49
I-50

## 4. Decisions
Decision Log
# | Decision | Date | Approved By | Decision Impacts | Comments
D-01 | SAMPLE - Change Request #003 approved to expand scope to include additional module functionality. | 2019-02-15 | Project Sponsor | Project will need to rebaseline budget and scheduled based on new scope.
D-02
D-03
D-04
D-05
D-06
D-07
D-08
D-09
D-10
D-11
D-12
D-13
D-14
D-15
D-16
D-17
D-18
D-19
D-20
D-21
D-22
D-23
D-24
D-25
D-26
D-27
D-28
D-29
D-30
D-31
D-32
D-33
D-34
D-35
D-36
D-37
D-38
D-39
D-40
D-41
D-42
D-43
D-44
D-45
D-46
D-47
D-48
D-49
D-50

## DropDowns (hidden)
Risk Register
Risk Type
Scope
Schedule
Budget
Resource
Quality
Technical
Other
ExposureRating
1
2
3
4
Risk Response
Accept
Transfer
Mitigate
Avoid
Issue Log
Issue Priority
High
Medium
Low